FINANCE-FIRST F&B PROJECTION ENGINE Phased Engineering Roadmap v3.0 Dark Kitchen ¦ Pizza ¦ Platform-Driven Delivery ¦ Finance-First Planning

| Document | Phased Engineering Roadmap v3.0 |
| --- | --- |
| Version | v3.0 — 2026-03-30 |
| Scope | 73 Core Tables ¦ 22 Screens ¦ 60 Weeks to Full v3 |
| Format | Dark Kitchen ¦ Pizza ¦ Finance-First Planning |

Architecture Layers

A – Planning Spine & Governance

B – Product & Market Reference

C – Commercial Driver Engine

D – Cost Driver Engine

E – Funding & Capital Strategy

F – Financial Projection Engine

G – KPI & Performance Intelligence

H – Risk & Uncertainty Framework

# Section 1 — Executive Roadmap Summary

The table below provides the end-to-end phased delivery plan. Each phase has a defined scope, milestone gate, and cumulative table/screen count.

| Phase | Weeks | Core Deliverable | Cumulative Tables | Cumulative Screens | Milestone Gate |
| --- | --- | --- | --- | --- | --- |
| Phase 0: Foundation | 1–4 | Infrastructure, schema bootstrap, auth, CI/CD | 0 | 0 | CI/CD Live |
| Phase 1: Planning Spine MVP | 5–12 | Planning spine, reference dimensions, scenario/version management | 8 | 3 | Version Control Live |
| Phase 2: Driver & Projection Engine | 13–24 | Commercial + cost + funding drivers, full P&L / Cash Flow / Balance Sheet | 32 | 10 | P&L Computed |
| Phase 3: Scenario & Intelligence | 25–36 | Scenario comparison, KPI engine, assumptions manager, driver explainability | 42 | 18 | Scenario Compare Live |
| Phase 4: Risk, Simulation & Capital | 37–48 | Risk framework, Monte Carlo, simulation lab, capital strategy | 58 | 24 | Monte Carlo Live |
| Phase 5: Governance & Portfolio | 49–60 | Full governance, decision memory, portfolio optimization | 66 | 28 | Governance Workflow |
| Phase 6: Operational Extensions | 61+ | Optional: orders, kitchen stations, intraday, actuals ingestion | 77 | 28 | Actuals Ingested |

Total Scope: 73 Core Tables, 22+ Core Screens, 60 Weeks to full v3 scope.

# Section 2 — Build Principles

1. Finance-first build order:  Build the planning spine before operational features.

2. Schema-first development:  Finalise table contracts before building APIs or UI.

3. Scenario-driven from day one:  Every data write must be scenario-aware.

4. No premature optimisation:  Avoid building operational granularity until financial model is proven.

5. Explicit interface contracts:  API contracts between services must be written before implementation begins.

6. Driver-before-actuals:  Projection engine must work end-to-end before actuals bridge is built.

7. Scope taxonomy enforcement:  Tag every ticket as Core v1 / Recommended v1.5 / Phase 2-3 / Optional Extension.

8. Milestone-gate discipline:  Each phase must pass its gate before the next phase begins.

# Section 3 — Phase 0: Foundation (Weeks 1–4)

Layer: Infrastructure & Schema Bootstrap

## Infrastructure Tasks

Cloud environment setup

CI/CD pipeline implementation

PostgreSQL database provisioning

Migration framework setup (Flyway / Liquibase)

Auth service implementation (JWT / OAuth2)

Monitoring and logging configuration

Staging environment deployment

## Schema Bootstrap Conventions

Multi-tenancy schema design

UUID primary key convention

Audit fields pattern (created_by, updated_at)

Soft delete pattern

DECIMAL(19,4) money convention

JSON extensibility columns

## Sprint Breakdown

| Sprint | Weeks | Deliverables |
| --- | --- | --- |
| Sprint 0.1 | Weeks 1–2 | Dev environment setup, cloud infrastructure provisioning, CI/CD pipeline configuration. |
| Sprint 0.2 | Weeks 3–4 | Auth service implementation, schema migration framework setup, base table conventions, admin scaffolding. |

Milestone Gate: CI/CD live, schema migrations automated, auth working, dev/staging environments stable.

# Section 4 — Phase 1: Planning Spine MVP (Weeks 5–12)

Layer: Planning Spine & Governance (Layer A)  +  Product & Market Reference (Layer B)

## Core Deliverables

| Tables (8) | companies, planning_calendars, planning_periods, scenarios, assumption_sets, plan_versions, markets, kitchens, platforms, product_families |
| --- | --- |
| APIs | CRUD for all planning spine entities, scenario create/clone, assumption set versioning, plan version freeze/publish |
| Screens (3) | Screen 01: Home / Global Planning Overview Screen 16: Plan Version Manager Screen 02: Executive Planning Cockpit (skeleton) |

## Sprint Breakdown

| Sprint | Weeks | Deliverables |
| --- | --- | --- |
| Sprint 1.1 | Weeks 5–6 | companies, planning_calendars, planning_periods — basic CRUD APIs. |
| Sprint 1.2 | Weeks 7–8 | scenarios, assumption_sets, plan_versions — versioning and clone logic. |
| Sprint 1.3 | Weeks 9–10 | markets hierarchy (country > cluster > macro > micro), kitchens, platforms, product_families. |
| Sprint 1.4 | Weeks 11–12 | Home screen, Plan Version Manager, Executive Cockpit skeleton, global scope/time/scenario selectors. |

Milestone Gate: Scenario and planning period CRUD complete, version control working, plan clone and freeze functional, reference dimensions seeded.

# Section 5 — Phase 2: Driver & Projection Engine (Weeks 13–24)

Layer: Commercial Drivers (C)  +  Cost Drivers (D)  +  Funding (E)  +  Financial Projections (F)

## Core Deliverables

| Tables (+24) Commercial | demand_drivers, price_plans, mix_plans, revenue_projection_lines, assumption_confidence |
| --- | --- |
| Tables (+24) Cost | unit_cost_profiles, labor_models, headcount_plans, opex_plans, marketing_plans, capex_plans, working_capital_policies |
| Tables (+24) Funding | equity_rounds, debt_facilities, debt_repayment_schedules, capital_allocation_plans, dilution_models |
| Tables (+24) Financial | pnl_projections, cashflow_projections, balance_sheet_projections, unit_economics_projections |
| APIs | Driver input CRUD, projection computation engine (P&L, Cash Flow, Balance Sheet), unit economics calculation, working capital modelling. |
| Screens (+7) | Screen 09: P&L Console Screen 10: Cash Flow Console Screen 11: Balance Sheet Console Screen 12: Unit Economics Console Screens 06–08: Assumptions Manager (Demand / Cost / Funding Tabs) |

## Sprint Breakdown

| Sprint | Weeks | Deliverables |
| --- | --- | --- |
| Sprint 2.1 | Weeks 13–14 | demand_drivers, price_plans, mix_plans + demand driver API. |
| Sprint 2.2 | Weeks 15–16 | unit_cost_profiles, labor_models, headcount_plans + cost driver API. |
| Sprint 2.3 | Weeks 17–18 | opex_plans, marketing_plans, capex_plans, working_capital_policies. |
| Sprint 2.4 | Weeks 19–20 | equity_rounds, debt_facilities, repayment schedules, dilution_models. |
| Sprint 2.5 | Weeks 21–22 | pnl_projections, cashflow_projections, balance_sheet_projections — computation engine build. |
| Sprint 2.6 | Weeks 23–24 | unit_economics_projections, Assumptions Manager screens, P&L / CF / BS / UE screens. |

Milestone Gate: P&L projection computable end-to-end from driver inputs, unit economics waterfall working, all financial statements rendering in UI.

# Section 6 — Phase 3: Scenario & Intelligence Layer (Weeks 25–36)

Layer: KPI & Performance Intelligence (Layer G) — partial build

## Core Deliverables

| Tables (+10) | kpi_projections, driver_explainability, variance_attribution, performance_alerts, competitor_profiles, assumption_confidence (enhance), scenario comparison views |
| --- | --- |
| APIs | KPI computation, scenario comparison engine, explainability engine (EBITDA bridge, revenue bridge), alert generation logic. |
| Screens (+8) | Screen 03: Scenario Comparison Console Screen 02: Executive Cockpit (Full) Screen 15: Driver Explainability Console Screen 10: Market Rollout Planner Screen 11: Market Attractiveness Scoring Screen 19: Demand Driver Console Screen 21: Trigger & Alert Dashboard |

## Sprint Breakdown

| Sprint | Weeks | Deliverables |
| --- | --- | --- |
| Sprint 3.1 | Weeks 25–26 | kpi_projections — all 21 KPI definitions and computation logic. |
| Sprint 3.2 | Weeks 27–28 | driver_explainability, variance_attribution — EBITDA and revenue bridges. |
| Sprint 3.3 | Weeks 29–30 | performance_alerts — threshold rules, severity coding, notification triggers. |
| Sprint 3.4 | Weeks 31–32 | Scenario Comparison Console, full Executive Cockpit integration. |
| Sprint 3.5 | Weeks 33–34 | Market Rollout Planner, Market Attractiveness Scoring, Driver Explainability Console. |
| Sprint 3.6 | Weeks 35–36 | Trigger & Alert Dashboard, Demand Driver Console, Assumptions Working Capital tab. |

Milestone Gate: Scenario comparison operational end-to-end, all 21 KPIs displaying correctly, EBITDA bridge and revenue bridge computable.

# Section 7 — Phase 4: Risk, Simulation & Capital (Weeks 37–48)

Layer: Risk & Uncertainty (H)  +  Simulation (I)  +  Funding Enhancement

## Core Deliverables

| Tables (+16) Risk | risk_objects, risk_scenarios, monte_carlo_runs, monte_carlo_summaries, trigger_log |
| --- | --- |
| Tables (+16) Simulation | simulation_scenarios, simulation_results, sensitivity_analyses, decision_memory, decision_log |
| Tables (+16) Capital | capital_allocation_plans (enhance), raise_recommendation_models, covenant_tracking, runway_optimization |
| APIs | Monte Carlo engine, sensitivity analysis, simulator run API, capital raise recommendation, funding strategy computation. |
| Screens (+6) | Screen 17: Risk Management Dashboard Screen 18: Simulation Lab Screen 04: Cash & Funding Console Screen 05: Capital Strategy Console Screen 12: Portfolio Optimization (partial) Screen 22: Decision Memory (partial) |

## Sprint Breakdown

| Sprint | Weeks | Deliverables |
| --- | --- | --- |
| Sprint 4.1 | Weeks 37–38 | risk_objects, risk_scenarios — risk taxonomy and registration. |
| Sprint 4.2 | Weeks 39–40 | monte_carlo_runs, monte_carlo_summaries — Monte Carlo compute engine. |
| Sprint 4.3 | Weeks 41–42 | sensitivity_analyses — tornado charts, sensitivity grids. |
| Sprint 4.4 | Weeks 43–44 | simulation_scenarios, simulation_results — simulation run framework. |
| Sprint 4.5 | Weeks 45–46 | Capital strategy: raise recommendation, runway optimisation, dilution modelling UI. |
| Sprint 4.6 | Weeks 47–48 | Risk Dashboard, Simulation Lab, Cash & Funding Console, Capital Strategy Console. |

Milestone Gate: Monte Carlo runnable end-to-end, capital strategy computing correctly, risk objects operational, simulation lab functional.

# Section 8 — Phase 5: Governance & Portfolio (Weeks 49–60)

Layer: Planning Spine Enrichment  +  Portfolio Construction (J)

## Core Deliverables

| Tables (+8) | governance_events, assumption_lineage, portfolio_plans, market_portfolio_scores, portfolio_capital_allocations, portfolio_return_metrics, decision_memory (enhance), approval_workflows |
| --- | --- |
| APIs | Governance workflow engine, approval state machine, portfolio optimisation, capital allocation across markets. |
| Screens (+4) | Screen 20: Planning Governance Dashboard Screen 22: Plan Version Manager (enhanced) Screen 12: Portfolio Optimisation Console (full) Screen 22: Decision Memory Browser (full) |

## Sprint Breakdown

| Sprint | Weeks | Deliverables |
| --- | --- | --- |
| Sprint 5.1 | Weeks 49–50 | governance_events, assumption_lineage — audit trail and lineage tracking. |
| Sprint 5.2 | Weeks 51–52 | Approval workflow engine: draft > review > approved > published state machine. |
| Sprint 5.3 | Weeks 53–54 | portfolio_plans, market_portfolio_scores — portfolio scoring framework. |
| Sprint 5.4 | Weeks 55–56 | portfolio_capital_allocations, portfolio_return_metrics — capital allocation optimisation. |
| Sprint 5.5 | Weeks 57–58 | Planning Governance Dashboard, enhanced Plan Version Manager. |
| Sprint 5.6 | Weeks 59–60 | Portfolio Optimisation Console, Decision Memory Browser — full build. |

Milestone Gate: Governance approval workflow complete, portfolio capital allocation computing, decision memory logging correctly, all v3 core features operational.

# Section 9 — Phase 6: Operational Extensions (Weeks 61+)

Note: These are optional extensions not part of the finance-first core but available for operational depth.

## Core Deliverables

| Tables (+11) | order_headers, order_lines, kitchen_stations, staff_roster, actual_ingestion_log, intraday_demand_buckets, operational_events, product_variants, modifier_types, ingredient_bom, recipe_histories |
| --- | --- |
| Trigger Criteria | When business has sufficient operational data for actuals ingestion, or when operational optimisation becomes the priority. |

## Sprint Breakdown

| Sprint | Weeks | Deliverables |
| --- | --- | --- |
| Sprint 6.1 | Week 61+ | actual_ingestion_log, order_headers, order_lines — actuals import framework. |
| Sprint 6.2 | Week 61+ | intraday_demand_buckets, operational_events — hour-level demand tracking. |
| Sprint 6.3 | Week 61+ | kitchen_stations, staff_roster — kitchen-level operational data. |
| Sprint 6.4 | Week 61+ | product_variants, modifier_types, ingredient_bom, recipe_histories — deep product data. |

# Section 10 — Table Delivery Mapping

Every database table mapped to its delivery phase and architecture layer.

| Phase | Layer | Tables |
| --- | --- | --- |
| Phase 1 | Planning Spine & Ref | companies, planning_calendars, planning_periods, scenarios, assumption_sets, plan_versions, markets, kitchens, platforms, product_families |
| Phase 2 | Drivers & Financials | demand_drivers, price_plans, mix_plans, revenue_projection_lines, assumption_confidence, unit_cost_profiles, labor_models, headcount_plans, opex_plans, marketing_plans, capex_plans, working_capital_policies, equity_rounds, debt_facilities, debt_repayment_schedules, capital_allocation_plans, dilution_models, pnl_projections, cashflow_projections, balance_sheet_projections, unit_economics_projections |
| Phase 3 | Intelligence | kpi_projections, driver_explainability, variance_attribution, performance_alerts, competitor_profiles, scenario_comparisons |
| Phase 4 | Risk & Simulation | risk_objects, risk_scenarios, monte_carlo_runs, monte_carlo_summaries, trigger_log, simulation_scenarios, simulation_results, sensitivity_analyses, decision_memory, decision_log, raise_recommendation_models, covenant_tracking, runway_optimization |
| Phase 5 | Governance & Portfolio | governance_events, assumption_lineage, portfolio_plans, market_portfolio_scores, portfolio_capital_allocations, portfolio_return_metrics, approval_workflows |
| Phase 6 | Extensions (Optional) | order_headers, order_lines, kitchen_stations, staff_roster, actual_ingestion_log, intraday_demand_buckets, operational_events, product_variants, modifier_types, ingredient_bom, recipe_histories |

# Section 11 — Screen Delivery Mapping

All 28 dashboard screens mapped to delivery phase and primary user.

| Phase | Screens | Primary User |
| --- | --- | --- |
| Phase 1 | Home/Overview, Plan Version Manager, Executive Cockpit (Skeleton) | Admin / CEO |
| Phase 2 | P&L Console, Cash Flow Console, Balance Sheet Console, Unit Economics, Assumptions Manager (Demand / Cost / Funding) | CFO / Analyst |
| Phase 3 | Scenario Comparison Console, Executive Cockpit (Full), Driver Explainability Console, Market Rollout Planner, Market Attractiveness Scoring, Demand Driver Console, Trigger & Alert Dashboard | CEO / CFO / COO |
| Phase 4 | Risk Management Dashboard, Simulation Lab, Cash & Funding Console, Capital Strategy Console, Portfolio Optimisation (Partial) | CFO / Risk Lead |
| Phase 5 | Planning Governance Dashboard, Plan Version Manager (Full), Portfolio Optimisation Console (Full), Decision Memory Browser | CFO / CEO |

# Section 12 — Module Dependency Map

Build-order dependencies between engine modules. Each module must be complete before its dependents are started.

| Module (Must Be Complete) | Enables / Unlocks |
| --- | --- |
| Planning Spine | All drivers, all projections, all screens |
| Demand Drivers | Revenue Projections, KPIs, Scenario Comparison |
| Cost Drivers | P&L, EBITDA, Unit Economics |
| Funding & Capital | Cash Flow, Balance Sheet, Capital Strategy |
| Financial Projections | KPI Layer, Scenario Comparison, Driver Explainability |
| KPI Layer | Executive Cockpit (full), Trigger Alerts |
| Risk Framework | Simulation Lab, Monte Carlo outputs |
| Simulation Layer | Decision Memory |
| Portfolio Layer | Capital Allocation Optimisation |

# Section 13 — Team Structure

Recommended team composition per phase. Roles are additive — earlier hires remain throughout.

| Phase | Team Size | Key Addition | Composition |
| --- | --- | --- | --- |
| Phase 0–1 | 4 | Core Team | 1 Tech Lead, 1 Backend Engineer, 1 Frontend Engineer, 1 Product Manager |
| Phase 2 | 6 | +1 Backend, +1 Data Engineer | Core team + 1 Backend Engineer + 1 Data Engineer |
| Phase 3 | 7 | +1 Frontend/UI Engineer | Phase 2 team + 1 Frontend / UI Engineer |
| Phase 4 | 8 | +1 Data Scientist / Quant | Phase 3 team + 1 Data Scientist / Quant Analyst |
| Phase 5 | 9 | +1 Backend Engineer | Phase 4 team + 1 Backend Engineer |

# Section 14 — Testing Strategy

Phase-by-phase testing requirements to ensure quality gates are met before advancing.

| Phase | Testing Scope |
| --- | --- |
| Phase 1 | Unit tests for CRUD; integration tests for scenario clone and version freeze logic. |
| Phase 2 | Computation accuracy tests for P&L / CF / BS / UE; driver input validation tests. |
| Phase 3 | KPI computation accuracy; scenario comparison diff tests; explainability output validation. |
| Phase 4 | Monte Carlo distribution validation; simulation repeatability; capital computation accuracy. |
| Phase 5 | Governance workflow state machine tests; portfolio optimisation correctness. |
| Phase 6 | Data ingestion accuracy; actuals vs projections variance computation. |

# Section 15 — Delivery Risk Register

Key delivery risks with likelihood, impact, and mitigations. Review at each phase gate.

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Scope creep into operational features before financial core is stable | Medium | High | Enforce scope taxonomy tagging; phase gate reviews. |
| Computation engine performance degradation at scale | Medium | High | Performance-test at Phase 2; design for async computation jobs. |
| Monte Carlo engine complexity underestimated | Low | High | Bring in quant / data science resource before Phase 4 begins. |
| Team bandwidth squeeze during Phase 2–3 overlap | Medium | Medium | Hire backend engineer before Phase 2 starts. |
| Driver model changes breaking projection recalculation | High | High | Version-lock driver inputs per scenario; recompute on version change only. |
| Schema migration errors in production | Low | High | Use forward-only migrations; maintain schema rollback scripts. |
| UI complexity explosion from 22 screens | Medium | Medium | Build design system and component library before Phase 2 UI begins. |

# Section 16 — Definition of Done (Per Phase)

Each phase must meet all criteria before the next phase commences. Gates are mandatory.

| Phase Gate | Definition of Done |
| --- | --- |
| Phase 0 > 1 | CI/CD live, schema migrations automated, auth working, dev/staging environments stable. |
| Phase 1 > 2 | Scenario CRUD complete, version control and clone functional, reference dimensions seeded. |
| Phase 2 > 3 | P&L, Cash Flow, and Balance Sheet computable end-to-end; unit economics rendering in UI. |
| Phase 3 > 4 | Scenario comparison operational; all 21 KPIs displaying correctly; EBITDA bridge and revenue bridge computable. |
| Phase 4 > 5 | Monte Carlo functional; capital strategy computing; risk objects operational; simulation lab live. |
| Phase 5 > 6 | Governance approval workflow complete; portfolio capital allocation computing; decision memory logging; all core v3 features operational. |